## Slide 1: HeD Pilots
Reportable Condition Knowledge Management System (RCKMS)
CDC/CSTE/APHL

## Slide 2: Pilot Team
Identify the members of your organization who will be supporting this pilot. If possible include the role he/she will play in the pilot and contact information
Name | Role | Email
Laura Conn | Pilot Sponsor | lconn@cdc.gov
Rita Altamore | SME | Rita.Altamore@DOH.WA.GOV
Catherine Staes | SME | catherine.staes@hsc.utah.edu
Shu McGarvey | Primary contact | smcgarvey@cdc.gov
Randheer Gerhot | Architect | rgi8@cdc.gov

## Slide 3: Goal of the Pilot
The Reportable Condition Knowledge Management project will act as an artifact provider. RCKMS will provide one to two HeD files, both for reporting Pertussis in San Diego, California. The file(s) will have information targeted for a type of provider (e.g., laboratory, hospital, healthcare provider). This pilot anticipates partnering with one to two artifact consumers who can assess if the content of the files provides the information necessary to ascertain if a report should be sent to public health, and if the structure of the files supports consumption into the partner’s EHR, LIMS, or LIS (or CDS component of those systems).
  Partners: 1-2 artifact consumers
  Outcomes:
    Assessment from Vendor/Integrator - does the structure of the information support consumption and presentation?
    Assessment from Clinician/Healthcare SME - does the content tell you if a report qualifies to be sent to public health, and include the ancillary information needed to provide the report?

## Slide 4: RCKMS HeD Pilot Scope
San Diego County
Pertussis
PH Reporters
RCKMS
Authoring Framework
Database
Who, What, When, Where, How
Structured Output
Design
Hospital Labs
LIMS
EHR
PH
Reports
Data Load
National, Clinical & Public Health Laboratories
LIMS
Ambulatory Care
EHR
HeD
- Triggering Criteria
- Reporting Actions
- Links
Evaluation of output file with Receivers
Data collection file
Transformation into
HeD file format
Transmission of HeD files to pilot partners
Database to HeD mapping
* Long term scope of RCKMS is included at end of presentation

## Slide 5: What portions of the IG are you Piloting
Section of IG | Specifics to Pilot | Notes
3.2 ECA Rules | RCKMS will provide knowledge artifacts in HeD format that include the specifications for reporting Pertussis cases or lab results to San Diego County Health Department. | The criteria for triggering a report of Pertussis to send to the San Diego County Health Dept will be included in an HeD file. Additional information will include: Timeframe for reporting Reporting Actions – preferred and acceptable methods to send the report References and Links

## Slide 6: Information Requirements
Criteria
  Lab Detection
  Epidemiologic
  Clinical
    Diagnostic
    Signs & Symptoms
  Demographic
  Jurisdiction
Timeframe
Reporting Actions
References and Links

## Slide 7: Example Criteria
 | lab Test finding/method Classification |  | send all results ? | If the results matter, what are the result requirements? |  |  |  | 
LAB DETECTION CRITERIA |  |  |  | interpretationRequirement | interpretation value set | organismRequirement | organismRequirement | numericValueRequirement
 |  | Test value set |  |  |  |  |  | operator
Isolation of Bordetella pertussis from a clinical specimen | Culture | Tst_BPert_Cult | no | "positive" | Int_pos | Bordetella pertussis | Rst_BPert_Pos | 
Results from any test specific for pertussis | Pertussis by any method | Tst_BPert | yes | [leave blank] |  |  |  | 
CLINICAL CRITERIA | Data Element | Value Set | Observation/Qualifier/Finding | Finding Value Set | operator | physical quantity | unit of measure | Should reporters send suspected cases as well as confirmed cases?
Suspect or confirmed diagnosis of pertussis | Diagnosis | DX_Pert | Status | Stat_case |  |  |  | yes
Pertussis as cause of death | Cause of death | Dth_Pert |  |  |  |  |  | no
Pertussis as a significant condition contributing to death | Contributing to death | Dth_Fact_Pert |  |  |  |  |  | no
Preliminary results

## Slide 8: Reporting Actions & Links
Reporting Actions
References and Links
lab reporting | clinician reporting -with lab data | clinican reporting - no lab data | title
no | no | no | Immediate phone call required
 |  |  | REPORTING ACTION
A | A | A | fax to epi program at SDDHHS
A | A | A | phone to epi program at SDDHHS
A | A | A | mail to epi program at SDDHHS
NA | P | P | manual entry into webform WebCMR
P | NA | NA | elr to SDDHHS
Disease Reporting Requirements for Health Care Providers | http://www.sdcounty.ca.gov/hhsa/programs/phs/community_epidemiology/disease_reporting_requirements_for_health_care_providers.html
Clinical Laboratory Reporting and Specimen Submission Guidelines | http://www.sdcounty.ca.gov/hhsa/programs/phs/community_epidemiology/disease_reporting_requirements_for_laboratorians.html

## Slide 9: Reporting Specifications
Who, What, When, Where and How of Reporting
Who – is required to report (e.g., Hospital, Healthcare Provider, Lab)
What- information should be used to decided if a report needs to be made
When – should the report be sent (e.g., 2 hr, 24 hr, 10 days)
Where – should the report be sent (e.g., local HD, state HD, and where within the HD)
How – should the report be sent (e.g., ELR, phone, fax, mail)
What – link to specification for information that should be included in the report

## Slide 10: Variation in Reporting Time Frames
Jurisdiction | Type of reporting facility | Reporting time frames |  |  |  |  | 
 |  | Immediately | 24 hours | 2 days | 3 days | 7 days | Monthly
Colorado | Laboratories Hospitals Providers |  |  |  |  |  | 
Utah | Laboratories Hospitals Providers |  |  |  |  |  | 
Washington | Laboratories Hospitals Providers |  |  |  |  |  | 

## Slide 11: Variation in Elevated Blood Lead Level Criteria
Relevant Jurisdiction | Blood lead level | Patient’s Age | Reporting time-frame
Utah | ≥10mg/dL < 10mg/dL | Any Any | 60 days No action – not reportable
Colorado | ≥10mg/dL < 10mg/dL ≥ 25mg/dL < 25mg/dL | ≤18 years ≤ 18 years > 18 years > 18 years | 7 working days 30 days 30 days No action – not reportable
Washington | ≥ 10mg/dL < 10mg/dL ≥25mg/dL < 25mg/dL | ≤15 years ≤ 15 years Any > 15 years | 2 working days 1 month 2 working days 1 month

## Slide 12: Sample Observations
Findings | Example
Events have varied levels of urgency in different jurisdictions | Brucellosis reportable by healthcare providers within: 7 days in Colorado, 3 days in Utah, and Immediate in Washington
A reportable event is not the same as a clinical condition | Clinical condition, `Influenza', associated with two reportable events: ‘Influenza-associated death in a person less than 18 years of age‘ ‘Influenza-associated hospitalization’
Reporting criteria for some events constrained by patient's age, pregnancy status, hospitalization status, and hospitalization duration | Haemophilus influenzae reportable in Washington only if the patient was less than 5 years of age Hepatitis B (positive surface antigen) reportable in Washington only if the patient was pregnant Influenza-associated hospitalization reportable in Utah only if the patient was hospitalized for more than 24 hours

## Slide 13: Identify the Use Case Actors Involved:
The pilot will involve the following participants from the healthcare ecosystem:
  Vendors (LIMS, LIS, EHR, CDS)
  System Integrators
  Standards Organizations
  Physicians/Provider SMEs
  Laboratory SMEs
  Public Health content providers

## Slide 14: Minimum Configuration
RCKMS has collected pertussis reporting specifications from San Diego County and 6 other jurisdictions. This data has been loaded into the RCKMS database. Initial efforts have been made to create a structured HQMF file for Healthcare Providers/Hospitals.
This pilot includes applying lessons learned from the HQMF effort to create an HeD formatted pertussis file for Healthcare Providers/Hospitals, and Laboratory reporters.
  San Diego County Pertussis HQMF file includes:
    Reporting criteria – laboratory diagnostic, clinical, epidemiological
    Links to key reference information
    Reporting actions and methods
  File will specify the reporting specifications that apply to each different type of reporter
Any required transport protocols will be determined in conjunction with artifact consumer, however, for this pilot, the key is validation of the HeD structure and content which does not rely on transport.
This pilot requires partnership with vendor(s) supporting public health reporting from Laboratories and Healthcare Providers/Hospitals. In addition, clinical subject matter expertise is required to validate content.

## Slide 15: Timeline
We anticipate that the detailed timeline will be built in conjunction with our vendor partner(s) for this pilot, but some initial very draft dates are suggested below:
Milestone | Target Date | Responsible Party
Create HeD file for San Diego County Pertussis | April 26, 2013 | HeD Pilot Team and RCKMS team
Kickoff and Build Timeline w/ Pilot Partner | May 8, 2013 | RCKMS Team and Pilot Partner
Provide HeD files & Briefing | May 8, 2013 | HeD Pilot Team and RCKMS team
Conclude Pilot | June 15, 2013 | RCKMS Team and Partner

## Slide 16: Success Criteria
Assessment from vendor(s) on structure of information provided in HeD file:
  Is content in a machine-processable format that can be consumed by vendor’s system?
  Once consumed, can content be presented to the clinician?
Assessment by public health reporter (laboratorian and clinician) on content included in files:
  Is this the right information for determining if a report qualifies for submission to public health?
  Is there information missing that would must/should be included?

## Slide 17: In Scope/Out of Scope
In Scope
  Working with 1-2 Vendors/Healthcare SMEs
  Producing HeD file(s) for San Diego County Pertussis
  HeD file to contain reporting specifications for San Diego County Pertussis:
    Reporting criteria (Laboratory diagnostic, Clinical, Epidemiological)
  HeD file content will be targeted at the following types of public health reporters:
    Laboratories
    Healthcare Provider/Hospital
  Mapping from the database to HeD to illustrate plan for automatic file generation
Out of scope
  Producing artifacts for other conditions or jurisdictions
  Automated generation of the HeD file
  Automated transport of the HeD file

## Slide 18: Questions/Needs
Please include those items you wish to consider any questions you have or hope the pilot addresses. Additionally, please include those items you need in order to succeed.(we will try to accommodate as many of these needs as possible within the scope of ONC, S&I and HeD)

## Slide 19: Helpful References
Use Case 1: http://wiki.siframework.org/Health+eDecisions+Use+Case
Implementation Guide for UC 1: http://wiki.siframework.org/Health+eDecisions+Harmonization+and+Standards+%28Implementation%29 (see the “Final Consensus and Harmonization”)
Pilots Wiki Page: http://wiki.siframework.org/Health+eDecisions+Pilots

## Slide 20: Appendix A: timeline details
Goal & Activities | Week Number | Tentative Dates | Deliverables
Kickoff /Establish Goals & Partnerships: - Review HeD Initiative Goals - Review Piloting Process & Resources - Define Value Statement - Define HeD Pilot Goals & Success Metrics - Establish & Approve Pilots - Develop Pilot Briefs | 1-2 (2wks) | 1/07-1/21 | -Wiki Capturing Pilot Deliverables -Established Partnerships -Documented Value Statements and Success Metrics -Documented Pilot Briefs
Pilot Configuration: - Establish Pilot Test Environment & Resources - Establish Pilot Implementation & Testing Process - Develop & Review Pilot Configuration | 3-4 (2 wks) | 1/28- 2/11 | Approved Pilot Briefs Committed Pilot Resources Documented & Reviewed Pilot Configuration Guide Weekly Feedback on Use-Cases & IG Alignment
Pilot Development : - Setup & Develop Pilot Prototypes - Review prototypes | 5-10 (6 wks or less depending on Pilot activity) | 2/11-3/25 | Weekly Pilot Development Status Updates Weekly Feedback on Use-Cases & IG Alignment Updates to Pilot Configuration Guides Prepare for HL7 UC 1 re-ballot
Pilot Testing & Showcase : - Complete Testing - Prepare Solution Showcase | 11-12 (2wks) | 4/1-4/15 | Weekly Pilot Testing Updates & KPIs Showcase
Pilot Wrap-up : - Develop Lessons Learned an ONC Feedback - Review Initiative Goal Alignment - Establish Next-Steps | 13-14 (2 wks) | 4/15-4/29 | -Documented ONC Feedback - Next Steps Action Plan

## Slide 21: RCKMS Long term Scope
Public Health State, Local, Territorial Agencies
PH Reporters
RCKMS
Authoring Framework
Subscription Management
Including Notifications
Database
Who, What, When, Where, How
Structured Output
Generator
Hospital Labs
LIMS
EHR
PH
Reports
Query/View
National, Clinical & Public Health Laboratories
LIMS
Ambulatory Care
EHR
HeD Compliant format
- Triggering Criteria
- Reporting Actions
- Links
Web Services
Evaluation of output file with Receivers